## Sheet1
Query | Answer | Page | Status
Dye penetrant test, Dye penetrant examination (PT), DPT, DPE | Item 3.1: PT/MT & Thickness verification for overlay & hard facing has activity PT/MT & Thickness verification for overlay & hard facing. ¦ has extent of supply 100%. ¦ requires reference document Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ requires verifying document Inspection Report / NDT Reports, RT Films. ¦ requires inspection agency Vendor: H. ¦ requires inspection agency TPIA: W*/R. ¦ requires inspection agency LTEH: R. ¦ requires inspection agency OWNER/PMC: R. ¦ has remarks Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. | 6 | Exact
Dye penetrant test, Dye penetrant examination (PT), DPT, DPE | Item 1.1: NDT / QA-QC Procedures has activity DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures has extent of supply 100%. ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures verifying document Approved NDT Procedures. ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - Vendor Hold (H). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - TPIA Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - LTEH Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - OWNER/PMC Review (R). ¦ Item 1.1: NDT / QA-QC Procedures has remarks Duly approved by NDT level III person. | 5 | Exact
Function test report | Item 5.7: Performance Check: Functional test of complete assembly (as applicable). Functional/Calibration Test on Valve, Positioner/Robotor, Actuator & Hand wheel & accessories mounted. (Stroke, Linearity & Hysteresis) Paint shade & DFT check ¦ covers extent 100% ¦ references document Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ verifies with Inspection reports ¦ inspection agency Vendor: Perform (P). TPIA: Witness (W). LTEH: Witness (W). OWNER/PMC: Review (R). ¦ has remarks . | 7 | Exact
Heat treatment chart, PWHT chart | Item 2.1: Material Identification and IGC Test verifying document MTC's / Lab report / Heat Treatment Charts. | 5 | Exact
Heat treatment process-Normalising | Item 1.1: NDT / QA-QC Procedures has activity NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures has extent of supply 100%. ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures verifying document Approved NDT Procedures. ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - Vendor Hold (H). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - TPIA Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - LTEH Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - OWNER/PMC Review (R). ¦ Item 1.1: NDT / QA-QC Procedures has remarks Duly approved by NDT level III person. | 5 | Approximate
Heat treatment temperature | Item 1.1: NDT / QA-QC Procedures has activity NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). | 5 | Partial
Hydro test / Pressure test standard | Item 5.1: Hydrostatic Shell Test: -At 1.5 times of max. Operating pressure. has extent of supply 100%. requires reference document Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598. has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598. requires verifying document Hydro test reports. requires inspection agency Vendor: P. requires inspection agency TPIA: RW. requires inspection agency LTEH: RW. requires inspection agency OWNER/PMC: R. | 6 | Exact
Hydro test / Pressure test standard | Item 5.2: Hydrostatic Seat leakage test references document Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598. | 7 | Exact
Hydro test / Pressure test standard | Item 1.1: NDT / QA-QC Procedures has activity NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. | 5 | Exact
Intergranular corrosion test | Item 2.1: Material Identification and IGC Test has activity a) Material Identification and review of MTC for - 3.1 Mill test certificates as per EN 10204 for Valve Body, Bonnet, Plug, Seat, closure member & trim material (Spray Head, Nozzle & Spindle), Bar/ Forging & Fasteners. 2.2 test certificate as per EN 10204 for non-pressure containing parts. b) IGC Test for all SS Material (As per approved datasheet). Item 2.1: Material Identification and IGC Test has extent of supply 100%. Item 2.1: Material Identification and IGC Test requires reference document Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards. Item 2.1: Material Identification and IGC Test has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards. Item 2.1: Material Identification and IGC Test verifying document MTC's / Lab report / Heat Treatment Charts. Item 2.1: Material Identification and IGC Test inspection agency - Vendor Hold (H). Item 2.1: Material Identification and IGC Test inspection agency - TPIA Review (R). Item 2.1: Material Identification and IGC Test inspection agency - LTEH Review (R). Item 2.1: Material Identification and IGC Test inspection agency - OWNER/PMC Review (R). Item 2.1: Material Identification and IGC Test has remarks . | 5 | Exact
Lab test report | Item 7.1: Manufacturer's test certificates for all bought out items, accessories & spares etc. has extent of supply 100%. references document Approved MR, Datasheet, GAD's and applicable Specs/Standards. has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/Standards. verifying document MTC, TC's / reports. inspection agency Vendor: Perform (P). inspection agency TPIA: Review (R). inspection agency LTEH: Review (R). inspection agency OWNER/PMC: Review (R). has remarks . | 8 | Exact
Lab test report | Item 5.2: Hydrostatic Seat leakage test has activity Hydrostatic Seat leakage test. covers extent 100%. references document Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598. has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598. verifies with Hydro test reports. inspection agency Vendor: Perform (P). TPIA: Witness (W). LTEH: Witness (W). OWNER/PMC: Review (R). has remarks . | 7 | Exact
Liquid penetrant test | Item 3.3: LPT/PT of Fillet weld Joint (As applicable)-soundness has activity LPT/PT of Fillet weld Joint (As applicable)-soundness. ¦ has extent of supply 100%. ¦ requires reference document Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ requires verifying document Inspection Report / NDT Reports, RT Films. ¦ requires inspection agency Vendor: H. ¦ requires inspection agency TPIA: W*/R. ¦ requires inspection agency LTEH: R. ¦ requires inspection agency OWNER/PMC: R. ¦ has remarks Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. | 6 | Exact
Non destructive report | Item 1.1: NDT / QA-QC Procedures has activity NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures has extent of supply 100%. ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures verifying document Approved NDT Procedures. ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - Vendor Hold (H). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - TPIA Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - LTEH Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - OWNER/PMC Review (R). ¦ Item 1.1: NDT / QA-QC Procedures has remarks Duly approved by NDT level III person. | 5 | Exact
PMI test report | Item 4.1: PMI Test - All types of valves, rupture disks, bodies, pipe, flanges & trim (Applicable for SS & AS material), bonnets & covers (as applicable) ¦ extent of supply 100% ¦ requires reference document Approved MR, Datasheet, GAD's and applicable Specs/ Standards. ¦ has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/ Standards. ¦ requires verifying document PMI reports ¦ requires inspection agency Vendor: P ¦ requires inspection agency TPIA: W* ¦ requires inspection agency LTEH: R ¦ requires inspection agency OWNER/PMC: R ¦ has remarks 100% PMI - review *10% PMI Witness | 6 | Exact
Radiography test, Radiography examination (RT) | Item 3.2: RT of Butt weld Joint (As applicable) - soundness ¦ activity: RT of Butt weld Joint (As applicable) - soundness ¦ extent of supply: 100% ¦ reference document: Approved MR, Datasheet, GAD's and applicable Specs/Standards ¦ acceptance criteria: Approved MR, Datasheet, GAD's and applicable Specs/Standards ¦ verifying document: Inspection Report / NDT Reports, RT Films ¦ inspection agency: Vendor: H, TPIA: W*/R, LTEH: R, OWNER/PMC: R ¦ remarks: Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. | 6 | Exact
Radiography test, Radiography examination (RT) | Item 1.1: NDT / QA-QC Procedures has activity DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures has extent of supply 100%. ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures verifying document Approved NDT Procedures. ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - Vendor Hold (H). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - TPIA Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - LTEH Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - OWNER/PMC Review (R). ¦ Item 1.1: NDT / QA-QC Procedures has remarks Duly approved by NDT level III person. | 5 | Exact
Ultrasonic test | Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) has activity UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm). Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) has extent of supply 100%. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires reference document Approved MR, Datasheet, GAD's and applicable Specs/Standards.. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) has acceptance criteria Approved MR, Datasheet, GAD's and applicable Specs/Standards.. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires verifying document Inspection Report / NDT Reports, RT Films. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires inspection agency Vendor: H. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires inspection agency TPIA: W*/R. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires inspection agency LTEH: R. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) requires inspection agency OWNER/PMC: R. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) has remarks Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. | 6 | Exact
Ultrasonic test | Item 1.1: NDT / QA-QC Procedures has activity DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable). ¦ Item 1.1: NDT / QA-QC Procedures has extent of supply 100%. ¦ Item 1.1: NDT / QA-QC Procedures requires reference document API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures has acceptance criteria API 598 ASME B 16.34 ASME Section V. ¦ Item 1.1: NDT / QA-QC Procedures verifying document Approved NDT Procedures. ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - Vendor Hold (H). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - TPIA Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - LTEH Review (R). ¦ Item 1.1: NDT / QA-QC Procedures inspection agency - OWNER/PMC Review (R). ¦ Item 1.1: NDT / QA-QC Procedures has remarks Duly approved by NDT level III person. | 5 | Exact
Weld Overlay, Stellite, stellited, Hard facing, Corrosion resistant overlay, Hardness | Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has activity WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair (As applicable). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has extent of supply 100%. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair requires reference document ASME Section IX. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has acceptance criteria ASME Section IX. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair verifying document Approved WPS, PQR & WPQ. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - Vendor Hold (H). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - TPIA Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - LTEH Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - OWNER/PMC Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has remarks Duly certified by Reputed TPIA. | 5 | Exact
Welding report, WPS, PQR, WPQR as per ASME or EN | Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has activity WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair (As applicable). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has extent of supply 100%. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair requires reference document ASME Section IX. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has acceptance criteria ASME Section IX. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair verifying document Approved WPS, PQR & WPQ. ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - Vendor Hold (H). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - TPIA Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - LTEH Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair inspection agency - OWNER/PMC Review (R). ¦ Item 1.2: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair has remarks Duly certified by Reputed TPIA. | 5 | Exact
Witness, Review, Hold, Perform | Perform Point "P" requires Manufacturer / Supplier shall 100% perform inspection check. | 4 | Exact
Witness, Review, Hold, Perform | Item 3.1: PT/MT & Thickness verification for overlay & hard facing - Remarks: Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. Item 3.2: RT of Butt weld Joint (As applicable) - soundness - Remarks: Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. Item 3.3: LPT/PT of Fillet weld Joint (As applicable)-soundness - Remarks: Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. Item 3.4: UT for Forging, Bar stock (Trim Parts- Plug, Seat & Spindle etc.] (above Ø50 mm) - Remarks: Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. Item 3.5: Physical & Visual Checks - Remarks: (empty). Item 4.1: PMI Test - Remarks: 100% PMI - review *10% PMI Witness. Item 5.1: Hydrostatic Shell Test - Remarks: (empty). | 6 | Exact
Witness, Review, Hold, Perform | Item 5.2: Hydrostatic Seat leakage test inspection agency Vendor: Perform (P). Item 5.2: Hydrostatic Seat leakage test inspection agency TPIA: Witness (W). Item 5.2: Hydrostatic Seat leakage test inspection agency LTEH: Witness (W). Item 5.2: Hydrostatic Seat leakage test inspection agency OWNER/PMC: Review (R). | 7 | Exact
Witness, Review, Hold, Perform | Item 6: Spares / Loose Items (as per PO) inspection agency Vendor: Perform (P). inspection agency TPIA: Witness (W). inspection agency LTEH: Review (R). inspection agency OWNER/PMC: Review (R). | 8 | Exact
precipitation hardening | No relevant information found | 6 | NotFound
precipitation hardening | No relevant information found | 7 | NotFound
precipitation hardening | No relevant information found | 4 | NotFound
precipitation hardening | No relevant information found | 1 | NotFound
precipitation hardening | No relevant information found | 5 | NotFound