## Sheet1
topic | questions | answer | page_num | source_text
| Dye penetrant test, Dye penetrant examination (PT), DPT, DPE | [3.1]: PT/MT & Thickness verification for overlay & hard facing. ¦ 100% ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Inspection Report / NDT Reports, RT Films ¦ H ¦ W*/R ¦ R ¦ R ¦ Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. --- [1.1]: Item No 1.1: Activity: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ Extent of supply: 100% ¦ Reference Document: API 598 ASME B 16.34 ASME Section V ¦ Acceptance Criteria: API 598 ASME B 16.34 ASME Section V ¦ Verifying Document: Approved NDT Procedures ¦ Inspection Agency: Vendor H, TPIA R, LTEH R, OWNER/PMC R ¦ Remarks: Duly approved by NDT level III person. | 5, 6
| Function test report | [5.7]: Performance Check: Functional test of complete assembly (as applicable). Functional/Calibration Test on Valve, Positioner/Robotor, Actuator & Hand wheel & accessories mounted. (Stroke, Linearity & Hysteresis) Paint shade & DFT check | 7
| Heat treatment chart, PWHT chart | [2.1]: 2.1¦a) Material Identification and review of MTC for - 3.1 Mill test certificates as per EN 10204 for Valve Body, Bonnet, Plug, Seat, closure member & trim material (Spray Head, Nozzle & Spindle), Bar/ Forging & Fasteners. 2.2 test certificate as per EN 10204 for non-pressure containing parts. b) IGC Test for all SS Material (As per approved datasheet)¦100%¦Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards.¦MTC's / Lab report / Heat Treatment Charts¦H¦R¦R¦R¦ | 5
| Heat treatment process-Normalising | [1.1]: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ 100% ¦ API 598 ASME B 16.34 ASME Section V ¦ API 598 ASME B 16.34 ASME Section V ¦ Approved NDT Procedures ¦ H ¦ R ¦ R ¦ R ¦ Duly approved by NDT level III person. | 5
| Heat treatment temperature | [1.1]: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable)¦API 598 ASME B 16.34 ASME Section V¦API 598 ASME B 16.34 ASME Section V¦Approved NDT Procedures¦H¦R¦R¦R¦Duly approved by NDT level III person. | 5
| Hydro test / Pressure test standard | [5.1]: Hydrostatic Shell Test: -At 1.5 times of max. Operating pressure. ¦ Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598 ¦ Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598 ¦ Hydro test reports ¦ P ¦ RW ¦ RW ¦ R --- [5.2]: Hydrostatic Seat leakage test¦100%¦Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598¦Approved MR, Datasheet, GAD's and applicable Specs/ Standards. API-598¦Hydro test reports¦P¦RW¦RW¦R --- [1.1]: Item No 1.1: Activity: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrotest, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ Reference Document: API 598 ASME B 16.34 ASME Section V ¦ Acceptance Criteria: API 598 ASME B 16.34 ASME Section V ¦ Verifying Document: Approved NDT Procedures | 5, 6, 7
| Intergranular corrosion test | [2.1]: b) IGC Test for all SS Material (As per approved datasheet) --- [11]: For AS & SS Material IGC test as per ASTM Practice "E" to be carried out, Additionally, Microscopic structure to be observed at 250X magnification for checking no carbide precipitation. | 5, 8
| Lab test report | [2.1]: 2.1¦a) Material Identification and review of MTC for - 3.1 Mill test certificates as per EN 10204 for Valve Body, Bonnet, Plug, Seat, closure member & trim material (Spray Head, Nozzle & Spindle), Bar/ Forging & Fasteners. 2.2 test certificate as per EN 10204 for non-pressure containing parts. b) IGC Test for all SS Material (As per approved datasheet)¦100%¦Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards.¦MTC's / Lab report / Heat Treatment Charts¦H¦R¦R¦R | 5
| Liquid penetrant test | [3.3]: LPT/PT of Fillet weld Joint (As applicable)-soundness¦100%¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Inspection Report / NDT Reports, RT Films¦H¦W*/R¦R¦R¦Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. --- [1.1]: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable)¦API 598 ASME B 16.34 ASME Section V¦API 598 ASME B 16.34 ASME Section V¦Approved NDT Procedures¦H¦R¦R¦R¦Duly approved by NDT level III person. | 5, 6
| Non destructive report | [7.1]: 7.1¦1. Manufacturer's test certificates for all bought out items, accessories & spares etc. 2. Material co-relation chart showing Make, Model number, Sr Number, MTC/TC Number, Heat number, Statutory Certificate (As Applicable). Calibration & Performance Certificates, NDT, Hydrottest, IBR certificates. other TCs & Certificates as required by Data Sheets and Proj. Specs.¦100%¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦MTC, TC's / reports¦P¦R¦R¦R¦ --- [1.1]: Item No 1.1 ¦ Activity: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrot est, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ Extent of supply: 100% ¦ Reference Document: API 598 ASME B 16.34 ASME Section V ¦ Acceptance Criteria: API 598 ASME B 16.34 ASME Section V ¦ Verifying Document: Approved NDT Procedures ¦ Inspection Agency: Vendor H, TPIA R, LTEH R, OWNER/PMC R ¦ Remarks: Duly approved by NDT level III person. | 5, 8
| PMI test report | [4]: PMI Test - All types of valves, rupture disks, bodies, pipe, flanges & trim (Applicable for SS & AS material), bonnets & covers (as applicable)¦100%¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦PMI reports¦P¦W*¦R¦R¦100% PMI - review *10% PMI Witness | 6
| Radiography test, Radiography examination (RT) | [3.2]: RT of Butt weld Joint (As applicable) - soundness ¦ 100% ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Inspection Report / NDT Reports, RT Films ¦ H ¦ W*/R ¦ R ¦ R ¦ Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. --- [1.1]: Item No 1.1 ¦ Activity: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrot est, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ Extent of supply: 100% ¦ Reference Document: API 598 ASME B 16.34 ASME Section V ¦ Acceptance Criteria: API 598 ASME B 16.34 ASME Section V ¦ Verifying Document: Approved NDT Procedures ¦ Inspection Agency: Vendor H, TPIA R, LTEH R, OWNER/PMC R ¦ Remarks: Duly approved by NDT level III person. | 5, 6
| Ultrasonic test | [3.4]: UT for Forging, Bar stock (Trim Parts-Plug, Seat & Spindle etc.) (above Ø50 mm)¦100%¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Approved MR, Datasheet, GAD's and applicable Specs/Standards.¦Inspection Report / NDT Reports, RT Films¦H¦W*/R¦R¦R¦Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. --- [1.1]: Item No 1.1 ¦ Activity: NDT / QA-QC Procedures: DPT, MT, RT, UT Hydrottest, Pneumatic test, Heat Treatment procedures etc. (As applicable) ¦ Extent of supply: 100% ¦ Reference Document: API 598 ASME B 16.34 ASME Section V ¦ Acceptance Criteria: API 598 ASME B 16.34 ASME Section V ¦ Verifying Document: Approved NDT Procedures ¦ Inspection Agency: Vendor H, TPIA R, LTEH R, OWNER/PMC R ¦ Remarks: Duly approved by NDT level III person. | 5, 6
| Weld Overlay, Stellite, stellited, Hard facing, Corrosion resistant overlay, Hardness | [1.2]: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair (As applicable) ¦ 100% ¦ ASME Section IX ¦ ASME Section IX ¦ Approved WPS, PQR & WPQ ¦ H ¦ R ¦ R ¦ R ¦ Duly certified by Reputed TPIA | 5
| Welding report, WPS, PQR, WPQR as per ASME or EN | [1.2]: WPS / PQR / WPQ for welded valves, Overlay, Stellite & Weld repair (As applicable)¦100%¦ASME Section IX¦ASME Section IX¦Approved WPS, PQR & WPQ¦H¦R¦R¦R¦Duly certified by Reputed TPIA | 5
| Witness, Review, Hold, Perform | [3 Definitions]: Perform Point "P"¦Manufacturer / Supplier shall 100% perform inspection check.¦Hold Point "H"¦Hold for Inspection and do not proceed. Fabrication shall be kept under hold until inspection has been performed or written clearance is obtained by Vendor. The work cannot proceed unless the Hold Point is cleared.¦Witness Point "W"¦Witness for Inspection Advise of inspection, Fabrication may be continued if inspector is not present after invitation issued in due time.¦Review Point "R"¦Review / Check / Verify documents. Review of Procedures / Test Reports / Certificates / Inspection Reports --- [5.7]: Performance Check: Functional test of complete assembly (as applicable). Functional/Calibration Test on Valve, Positioner/Robotor, Actuator & Hand wheel & accessories mounted. (Stroke, Linearity & Hysteresis) Paint shade & DFT check ¦ 100% ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Inspection reports ¦ P ¦ W ¦ W ¦ R --- [3.5]: Physical & Visual Checks which includes: Markings, Overall dimensions, Face to face body dimension, Flanges verification, Thickness check, Checks for accessories, connections & installations. Functional checks on complete valve with all accessories. ¦ 100% ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Approved MR, Datasheet, GAD's and applicable Specs/Standards. ¦ Inspection Report ¦ H ¦ W ¦ R ¦ R ¦ Review of RT films, RT, UT, PT reports to be provided for review for 100%. *10% witness by TPIA. --- [7.1]: Item No 7.1: Documents Review. Activity: 1. Manufacturer's test certificates for all bought out items, accessories & spares etc. 2. Material co-relation chart showing Make, Model number, Sr Number, MTC/TC Number, Heat number, Statutory Certificate (As Applicable). Calibration & Performance Certificates, NDT, Hydrotect, IBR certificates. other TCs & Certificates as required by Data Sheets and Proj. Specs. Extent of supply: 100%. Reference Document: Approved MR, Datasheet, GAD's and applicable Specs/Standards. Acceptance Criteria: Approved MR, Datasheet, GAD's and applicable Specs/Standards. Verifying Document: MTC, TC's / reports. Inspection Agency: Vendor-P, TPIA-R, LTEH-R, OWNER/PMC-R. Remarks: None. | 4, 6, 7, 8
| precipitation hardening | []: No relevant information found --- []: No relevant information found --- []: No relevant information found --- [2.1]: Material Identification and review of MTC for - 3.1 Mill test certificates as per EN 10204 for Valve Body, Bonnet, Plug, Seat, closure member & trim material (Spray Head, Nozzle & Spindle), Bar/ Forging & Fasteners. 2.2 test certificate as per EN 10204 for non-pressure containing parts. b) IGC Test for all SS Material (As per approved datasheet) ¦ 100% ¦ Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards. ¦ Approved MR, Datasheet, GAD's and applicable Specs ASTM/ASME/Standards. ¦ MTC's / Lab report / Heat Treatment Charts ¦ H ¦ R ¦ R ¦ R --- []: No relevant information found | 1, 4, 5, 6, 7